Year 1 – Lessons Learned

Coaching and Demonstration Sites: Lessons Learned in Colorado

Phil Strain (phil.strain@ucdenver.edu); Laurie Beckel (lfbeckel@aol.com)

- Takes more time to get to fidelity of implementation (of practices) than expected

- Important to coordinate with other data needs/requirements

- Important to respond to varying learning styles of implementers

- Do not confuse by coaching on multiple initiatives

- TPOT can be used as personnel development tool

- Importance of building relationships!

- Coach training and role clarification is necessary for efficiency and success

- All levels and dimensions of program must be Pyramid Model knowledgeable and supportive

Considerations in Selecting Demo Sites

- State Team members should be in agreement as to nominated sites

- Sites should have strong administrative leadership that is committed to Pyramid and fidelity of implementation

- Sites should have a history of adopting and sustaining best practices; be of high quality

- Sites need to be OK with a multi-year commitment

- Implementers at sites must be expert with and excited about Pyramid Model

- Implementers need time to be coached!

Considerations in Selecting Coaches

- Deep knowledge of Pyramid content is essential

- Coaches must understand the notion of coaching to fidelity

- Coaches need to be “in love” with Pyramid Model

- Coaches need to commit first to coaching on the Pyramid Model

- Coaches need time to coach to fidelity including at least weekly contact with sites

- Coaches have a unique set of skills and activities used in coaching…training and support for these is essential

Data Collection

- SSRS: completed yearly on pre-post basis for all children in demo sites. Takes about 12 min./child for teacher to complete. Can also be used a social emotional screening tool and an OSEP outcome measure

- TPOT: completed on a pre-post basis at each demo site by coaches. Takes about 4 days to complete. Can also be used as a personnel feedback/assessment/evaluation tool

- BIR: Completed by “teachers” for each serious behavior occurrence. Takes about 1 minute to complete.

- Coaching log: completed by all coaches after each visit. Takes about 1 minute to complete.

Demonstration Site Experiences

Fremont County Head Start 	Chris Henager (chris.henager@piopc.net)

Accomplishments

- All Head Start staff trained on Pyramid

- Interest and plans for community-wide expansion

- Significant reductions in behavior support referrals

- Significant increase in confidence displayed by staff

- Kids talk the talk and walk the walk!

Challenges

- Time constraints

- Coaching on multiple “models”

- Communicating fit among “models”

- Effort needed on T-POT

Lessons Learned

- It takes lots of time!

- Important to streamline other jobs performed by coaches

- Cannot do “drive-by” training on Pyramid

Mesa County School District	Kim Self (kself@mesa.k12.co.us)

Accomplishments

- Model site implementing components at high fidelity

- Continuing to plan to get better

- Exposure to demo site resulted in community-wide scale-up for 2008-2009

Challenges

- Person-power/time needed to get to fidelity

- Person-power/time needed for scale-up

Lessons Learned

- Important to build relationships with Demo team

- Important to learn about individual learning styles

- Demo site staff are excited and proud

Creative Options	Denny McGihon (dmcgihon@cpco.org)

Value of the Pyramid Model

- Pyramid gives a model of strategies that work

- Pyramid is consistent with Head Start mandates

- Pyramid provides a common language

- Pyramid provides a unified approach--no more 100 different trainings

- Requires administrators to model the positive outlook and language to be used by staff

Challenges

- It takes time!

- Requires on-going training and supervision (coaching)

- Organizational buy-in required from the top

- Need regular time for staff meetings

- Data gathering is a challenge—adequate time

Lessons Learned

- Pyramid changes adults in major ways

- Family piece is essential to success and continuity

- Need to build in more staff time to collaborate/plan

- Need to keep it fresh, humorous, individualized while keeping fidelity to the model